## ap_data
LN | FA RO | FA RO to B1R | Total Counters | TankStatus | Ceilings | Initial Tests Run | BTG_tot | BTG_p0 | BTG_p1 | BTG_p2 | BTG_p3 | BTG_engines | BTG_doors | BTG_test | P3_Engine Hang | P3_Flight Controls | P3_Gear Swing | P3_Medium Pressure Test | P3_Oil On | P3_Power On | P3_Engine_Type | P3_Milestone_Completion_Percentage | shakes_complete | shakes_req
1 | 2025-06-26 | 51 | 60 | 1 | 0.90909 | 0.62 | 120 | 7 | 4 | 33 | 30 | 3 | 12 | 7 | 2 | 6 | 1 | 2 | 1 | 1 | RR | 1 | 1 | 3
2 | 2024-08-13 | 33 | 60 | 0 | 0.77273 | 0.82 | 141 | 4 | 31 | 22 | 21 | 5 | 1 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0
3 | 2024-08-16 | 69 | 42 | 0 | 0.90909 | 0.74 | 76 | 8 | 12 | 14 | 24 | 4 | 2 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0
4 | 2024-08-26 | 32 | 76 | 0 | 0.86364 | 1 | 101 | 7 | 30 | 1 | 35 | 11 | 0 | 7 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0
5 | 2025-08-14 | 53 | 61 | 0 | 0.90909 | 0.64 | 78 | 6 | 10 | 29 | 25 | 5 | 3 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | RR | 1 | 0 | 1
6 | 2024-08-30 | 40 | 39 | 1 | 1 | 1 | 50 | 7 | 2 | 11 | 25 | 15 | 4 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0
7 | 2024-09-08 | 40 | 55 | 0 | 0.81818 | 0.62 | 57 | 8 | 21 | 13 | 38 | 15 | 5 | 6 | 2 | 5 | 1 | 2 | 1 | 1 | GE | 0.83333 | 0
8 | 2024-09-16 | 40 | 57 | 0 | 1 | 0.98 | 88 | 15 | 23 | 4 | 22 | 5 | 0 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0
9 | 2024-09-19 | 33 | 52 | 0 | 0.90909 | 0.89 | 56 | 12 | 21 | 7 | 27 | 8 | 1 | 3 | 2 | 2 | 1 | -1 | 1 | 1 | RR | 0.8 | 0
10 | 2025-02-28 | 50 | 44 | 1 | 0.95455 | 0.72 | 84 | 9 | 4 | 25 | 29 | 2 | 5 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | RR | 1 | 0 | 7
11 | 2024-10-03 | 30 | 36 | 0 | 0.72727 | 0.62 | 65 | 9 | 11 | 45 | 28 | 4 | 1 | 4 | 2 | 5 | -1 | 2 | 1 | 1 | GE | 0.8 | 3 | 7
12 | 2024-10-10 | 179 | 51 | 0 | 0.86364 | 0.62 | 84 | 5 | 25 | 44 | 14 | 2 | 1 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 7
13 | 2024-10-15 | 31 | 27 | 0 | 0.90909 | 0.92 | 88 | 6 | 11 | 7 | 19 | 5 | 0 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 5 | 6
14 | 2024-10-24 | 34 | 47 | 0 | 0.90909 | 0.67 | 75 | 4 | 13 | 21 | 22 | 3 | 0 | 3 | 1 | 6 | -1 | 2 | 1 | 1 | GE | 0.8 | 4 | 7
15 | 2024-10-25 | 36 | 56 | 0 | 0.95455 | 0.68 | 147 | 6 | 17 | 21 | 34 | 6 | 5 | 2 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 4 | 7
16 | 2024-11-05 | 36 | 45 | 0 | 1 | 0.7 | 97 | 4 | 14 | 10 | 19 | 2 | 1 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 7 | 7
17 | 2024-11-08 | 31 | 63 | 0 | 1 | 0.5 | 65 | 3 | 23 | 13 | 31 | 6 | 0 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 1 | 1
18 | 2024-11-18 | 33 | 42 | 0 | 0.90909 | 0.59 | 84 | 0 | 6 | 7 | 31 | 2 | 2 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 7
19 | 2024-11-23 | 48 | 67 | 0 | 0.90909 | 0.54 | 204 | 5 | 29 | 20 | 31 | 2 | 2 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 7
20 | 2025-01-13 | 51 | 66 | 0 | 1 | 0.72 | 71 | 8 | 24 | 15 | 30 | 6 | 3 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 7
21 | 2024-12-03 | 53 | 93 | 0 | 0.72727 | 0.64 | 96 | 4 | 48 | 13 | 47 | 13 | 7 | 7 | 2 | 5 | -1 | 2 | 1 | 1 | GE | 0.8 | 0 | 7
22 | 2024-12-13 | 40 | 36 | 0 | 0.95455 | 0.84 | 53 | 5 | 8 | 8 | 30 | 7 | 2 | 3 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 1 | 7
23 | 2024-12-18 | 40 | 54 | 0 | 0.95455 | 0.77 | 124 | 3 | 15 | 16 | 30 | 8 | 6 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 8
24 | 2025-01-06 | 47 | 50 | 0 | 1 | 0.8 | 56 | 4 | 16 | 10 | 28 | 3 | 6 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 6
25 | 2025-01-20 | 39 | 47 | 0 | 0.95455 | 0.82 | 84 | 6 | 6 | 15 | 21 | 7 | 2 | 2 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 4 | 8
26 | 2025-01-29 | 45 | 42 | 0 | 1 | 0.92 | 62 | 10 | 7 | 8 | 24 | 6 | 0 | 0 | 2 | 6 | -1 | 2 | 1 | 1 | GE | 1 | 0 | 6
27 | 2025-02-04 | 51 | 51 | 0 | 0.86364 | 0.68 | 83 | 3 | 18 | 9 | 21 | 2 | 3 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 8
28 | 2025-02-10 | 44 | 45 | 0 | 0.95455 | 0.7 | 78 | 6 | 10 | 13 | 20 | 4 | 3 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 8
29 | 2025-02-17 | 48 | 42 | 0 | 0.95455 | 0.89 | 75 | 5 | 12 | 9 | 20 | 6 | 3 | 0 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 6
30 | 2025-02-22 | 42 | 35 | 1 | 0.95455 | 0.86 | 96 | 5 | 10 | 17 | 15 | 3 | 3 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 7
31 | 2025-03-07 | 46 | 26 | 1 | 1 | 0.87 | 68 | 4 | 7 | 8 | 24 | 8 | 3 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 7
32 | 2025-03-13 | 45 | 40 | 1 | 0.86364 | 0.77 | 89 | 2 | 9 | 19 | 27 | 2 | 5 | 3 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 0 | 7
33 | 2025-03-19 | 52 | 38 | 1 | 0.95455 | 0.68 | 57 | 2 | 4 | 22 | 19 | 2 | 5 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 6
34 | 2025-03-25 | 55 | 33 | 0 | 0.90909 | 0.64 | 85 | 7 | 4 | 22 | 21 | 2 | 2 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 1 | 7
35 | 2025-03-31 | 45 | 28 | 0 | 0.95455 | 0.67 | 29 | 3 | 5 | 13 | 16 | 2 | 3 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 1 | 7
36 | 2025-04-04 | 42 | 35 | 1 | 0.90909 | 0.68 | 77 | 1 | 4 | 18 | 22 | 3 | 4 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 1 | 7
37 | 2025-04-15 | 49 | 40 | 0 | 0.90909 | 0.72 | 68 | 1 | 14 | 18 | 17 | 3 | 6 | 4 | 2 | 4 | 1 | 2 | 1 | 1 | GE | 0.83333 | 3 | 6
38 | 2025-04-18 | 41 | 19 | 1 | 1 | 0.8 | 24 | 0 | 2 | 13 | 17 | 4 | 1 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 5 | 7
39 | 2025-04-25 | 47 | 32 | 0 | 1 | 0.8 | 38 | 5 | 6 | 15 | 18 | 3 | 2 | 3 | 2 | 5 | 1 | 2 | 1 | 1 | GE | 0.83333 | 0 | 7
40 | 2025-05-01 | 46 | 46 | 0 | 0.95455 | 0.83 | 49 | 0 | 21 | 16 | 15 | 2 | 7 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 8
41 | 2025-05-07 | 47 | 60 | 0 | 0.95455 | 0.68 | 68 | 4 | 27 | 20 | 26 | 2 | 6 | 5 | 2 | 2 | 1 | 2 | 1 | 1 | GE | 0.83333 | 0 | 8
42 | 2025-05-14 | 48 | 61 | 0 | 1 | 0.57 | 77 | 3 | 16 | 25 | 24 | 5 | 9 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 8
43 | 2025-05-21 | 45 | 47 | 1 | 1 | 0.51 | 80 | 3 | 3 | 24 | 24 | 2 | 9 | 7 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 8
44 | 2025-05-28 | 44 | 51 | 1 | 0.81818 | 0.64 | 58 | 11 | 6 | 28 | 24 | 4 | 6 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 8
45 | 2025-06-02 | 55 | 46 | 1 | 0.90909 | 0.71 | 56 | 5 | 7 | 24 | 27 | 6 | 3 | 5 | 2 | 6 | -1 | 2 | 1 | 1 | GE | 1 | 0 | 7
46 | 2025-06-09 | 46 | 37 | 1 | 0.90909 | 0.7 | 73 | 2 | 10 | 23 | 15 | 1 | 6 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 8
47 | 2025-06-12 | 31 | 59 | 0 | 0.86364 | 0.67 | 68 | 4 | 8 | 36 | 17 | 2 | 14 | 5 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0
48 | 2025-06-17 | 38 | 42 | 1 | 0.86364 | 0.71 | 68 | 4 | 5 | 25 | 25 | 3 | 7 | 4 | 2 | 6 | 1 | 2 | -1 | 1 | GE | 1 | 0 | 6
49 | 2025-06-20 | 47 | 74 | 0 | 0.86364 | 0.62 | 113 | 5 | 11 | 41 | 31 | 4 | 9 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 3 | 7
50 | 2025-07-01 | 41 | 56 | 0 | 0.81818 | 0.66 | 98 | 13 | 10 | 24 | 25 | 4 | 9 | 5 | 2 | 6 | 1 | 2 | 1 | -1 | GE | 1 | 2 | 6
51 | 2025-07-08 | 39 | 77 | 0 | 0.90909 | 0.71 | 110 | 5 | 29 | 24 | 27 | 2 | 6 | 2 | 2 | 6 | -1 | 2 | 1 | 1 | GE | 1 | 2 | 8
52 | 2025-07-11 | 51 | 67 | 0 | 0.90909 | 0.69 | 94 | 8 | 11 | 29 | 24 | 3 | 9 | 7 | 2 | 2 | -1 | 2 | -1 | 1 | GE | 0.75 | 0
53 | 2025-07-17 | 54 | 80 | 0 | 0.81818 | 0.47 | 132 | 12 | 5 | 43 | 33 | 4 | 7 | 8 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 8
54 | 2025-07-22 | 39 | 67 | 1 | 0.86364 | 0.68 | 102 | 9 | 4 | 37 | 26 | 3 | 6 | 5 | 2 | 6 | -1 | 2 | 1 | 1 | GE | 1 | 1 | 7
55 | 2025-07-29 | 52 | 58 | 1 | 0.77273 | 0.59 | 124 | 7 | 4 | 39 | 21 | 2 | 8 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 3 | 8
56 | 2025-08-01 | 42 | 59 | 0 | 0.77273 | 0.81 | 61 | 8 | 8 | 35 | 23 | 7 | 5 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 3 | 7
57 | 2025-08-11 | 54 | 60 | 0 | 0.90909 | 0.76 | 103 | 7 | 3 | 35 | 21 | 3 | 5 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 8
58 | 2025-08-22 | 34 | 38 | 0 | 1 | 0.9 | 82 | 3 | 5 | 17 | 22 | 6 | 6 | 1 | 1 | 6 | 1 | 2 | 1 | 1 | GE | 0.83333 | 1 | 7
59 | 2025-08-19 | 44 | 71 | 0 | 0.72727 | 0.88 | 96 | 9 | 13 | 37 | 14 | 3 | 7 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 8
60 | 2025-09-02 | 41 | 54 | 0 | 0.81818 | 0.72 | 88 | 3 | 10 | 26 | 31 | 5 | 3 | 4 | 2 | 6 | -1 | 2 | 1 | 1 | GE | 1 | 0 | 7
61 | 2025-08-26 | 68 | 101 | 0 | 0.77273 | 0.56 | 185 | 15 | 14 | 71 | 40 | 9 | 8 | 5 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 8
62 | 2025-09-11 | 74 | 67 | 0 | 0.72727 | 0.56 | 107 | 3 | 10 | 46 | 22 | 2 | 3 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 8
63 | 2025-09-06 | 62 | 85 | 0 | 0.54545 | 0.52 | 102 | 16 | 4 | 52 | 26 | 4 | 3 | 5 | 2 | 5 | 1 | 2 | 1 | 1 | GE | 0.83333 | 0 | 8
64 | 2025-09-17 | 32 | 27 | 1 | 0.86364 | 0.85 | 95 | 3 | 3 | 15 | 18 | 4 | 4 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 5 | 7
65 | 2025-09-23 | 30 | 39 | 1 | 0.95455 | 0.73 | 58 | 3 | 2 | 21 | 26 | 4 | 6 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 6
66 | 2025-09-26 | 31 | 63 | 1 | 0.77273 | 0.56 | 82 | 7 | 2 | 34 | 26 | 2 | 6 | 5 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 7
67 | 2025-10-02 | 33 | 44 | 1 | 0.57143 | 0.66 | 71 | 0 | 3 | 27 | 25 | 3 | 5 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 7
68 | 2025-10-08 | 36 | 49 | 1 | 0.77273 | 0.7 | 83 | 4 | 2 | 29 | 22 | 4 | 6 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 3 | 7
69 | 2025-10-14 | 32 | 37 | 1 | 0.95455 | 0.77 | 50 | 0 | 8 | 17 | 26 | 6 | 6 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 6
70 | 2025-10-17 | 35 | 50 | 1 | 0.81818 | 0.72 | 61 | 0 | 4 | 21 | 27 | 8 | 7 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 1 | 7
71 | 2025-10-23 | 49 | 68 | 0 | 0.90909 | 0.63 | 94 | 2 | 9 | 34 | 24 | 9 | 8 | 3 | 1 | 6 | 1 | 2 | 1 | 1 | GE | 0.83333 | 0 | 8
72 | 2025-11-02 | 21 | 32 | 1 | 1 | 0.8 | 87 | 0 | 2 | 16 | 16 | 2 | 6 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | RR | 1 | 7 | 7
73 | 2025-11-13 | 34 | 37 | 0 | 0.95455 | 0.74 | 51 | 0 | 5 | 21 | 16 | 5 | 7 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 5
74 | 2025-11-10 | 27 | 29 | 1 | 0.90909 | 0.8 | 60 | 0 | 2 | 14 | 14 | 1 | 3 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | RR | 1 | 6 | 7
75 | 2025-11-18 | 41 | 48 | 1 | 0.86364 | 0.62 | 119 | 1 | 1 | 30 | 27 | 5 | 7 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 8
76 | 2025-11-23 | 68 | 35 | 1 | 0.90909 | 0.7 | 46 | 0 | 5 | 16 | 17 | 3 | 6 | 2 | 2 | 6 | 1 | 2 | 1 | 1 | RR | 1 | 7 | 7
77 | 2025-11-30 | 74 | 45 | 0 | 0.90909 | 0.8 | 97 | 1 | 4 | 30 | 17 | 1 | 4 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 8
78 | 2025-12-03 | 62 | 47 | 1 | 0.77273 | 0.72 | 73 | 2 | 4 | 27 | 19 | 3 | 5 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 7 | 7
79 | 2025-12-07 | 32 | 35 | 1 | 0.95455 | 0.78 | 69 | 3 | 3 | 24 | 19 | 3 | 5 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 0 | 6
80 | 2025-12-11 | 30 | 55 | 0 | 0.77273 | 0.69 | 130 | 4 | 10 | 37 | 23 | 2 | 6 | 3 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 6 | 8
81 | 2025-12-15 | 31 | 63 | 0 | 0.77273 | 0.78 | 95 | 4 | 7 | 36 | 22 | 2 | 3 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 5 | 8
82 | 2025-12-18 | 33 | 56 | 0 | 0.86364 | 0.71 | 93 | 4 | 8 | 36 | 21 | 4 | 5 | 4 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 7 | 8
83 | 2025-12-22 | 36 | 62 | 0 | 0.90909 | 0.73 | 106 | 3 | 8 | 33 | 28 | 4 | 8 | 4 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 4 | 7
84 | 2026-01-07 | 32 | 54 | 1 | 0.81818 | 0.58 | 89 | 2 | 5 | 30 | 26 | 2 | 7 | 5 | 2 | 6 | 1 | 1 | 1 | 1 | GE | 0.83333 | 4 | 8
85 | 2026-01-11 | 35 | 61 | 1 | 0.66667 | 0.88 | 97 | 2 | 4 | 7 | 9 | 1 | 1 | 1 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 5 | 7
86 | 2026-01-14 | 49 | 79 | 0 | 0.63636 | 0.67 | 139 | 4 | 26 | 36 | 28 | 4 | 7 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 8
87 | 2026-01-16 | 44 | 61 | 0 | 0.59091 | 0.61 | 93 | 2 | 11 | 30 | 26 | 4 | 5 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 2 | 7
88 | 2026-01-21 | 48 | 64 | 0 | 0.59091 | 0.75 | 98 | 3 | 16 | 24 | 24 | 1 | 6 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 5 | 7
89 | 2026-01-23 | 42 | 106 | 0 | 0.45455 | 1 | 138 | 6 | 30 | 6 | 15 | 5 | 0 | 6 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 4 | 7
90 | 2026-01-27 | 46 | 66 | 0 | 0.45455 | 0.96 | 96 | 3 | 15 | 6 | 11 | 4 | 0 | 4 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 3 | 7
91 | 2026-01-29 | 45 | 71 | 0 | 0.63636 | 0.73 | 99 | 5 | 12 | 33 | 26 | 6 | 7 | 5 | 2 | 6 | 1 | 2 | 1 | 1 | GE | 1 | 3 | 6
92 | 2026-02-05 | 52 | 69 | 0 | 0.59091 | 0.73 | 97 | 3 | 5 | 41 | 23 | 1 | 9 | 5 | 2 | 4 | -1 | 2 | 1 | 1 | GE | 0.8 | 4 | 8
93 | 2026-02-09 | 47 | 80 |  | 0.45455 | 0.76 | 130 | 8 | 13 | 41 | 30 | 3 | 8 | 6 | [8 empty] | 5 | 7

## location_data
Location | Future State Priority | Date Online | Owner | tooling_jacking | tooling_wings | tooling_tankClosure | centerline_dependencies | obstructions | notes
D1 | 99 | Now | DC | FALSE | FALSE | FALSE
D2 | 99 | Now | DC | FALSE | FALSE | FALSE
A1 | 17 | Now | DC | TRUE | TRUE | FALSE
A2 | 17 | Now | DC | TRUE | TRUE | FALSE
A3 | 17 | Now | DC | TRUE | TRUE | FALSE
A4 | 17 | Now | DC | TRUE | TRUE | FALSE
A5 | 17 | Now | DC | TRUE | TRUE | FALSE
A6 | 17 | Now | DC | TRUE | TRUE | FALSE
A7 | 17 | Now | DC | TRUE | TRUE | FALSE
A8 | 17 | Now | DC | TRUE | TRUE | FALSE
A9 | 26 | Now | DC | TRUE | TRUE | FALSE | C1
A10 | 17 | Now | DC | TRUE | TRUE | FALSE | C1, C2
L4 | 5 | Now | FA | FALSE | TRUE | TRUE
L5 | 6 | Now | FA | FALSE | FALSE | TRUE | L4
CR1 | 9 | Now |  | FALSE | FALSE | FALSE | CR3, CR2
CR2 | 9 | Now |  | FALSE | FALSE | FALSE | CR3
CR3 | 9 | Now |  | FALSE | FALSE | FALSE
C1 | 16 | Now | FA | FALSE | FALSE | FALSE
C2 | 15 | Now | FA | FALSE | FALSE | FALSE | C1
C3 | 12 | Now | FA | FALSE | FALSE | FALSE | C1, C2
C4 | 12 | Now | FA | FALSE | FALSE | FALSE | C1, C2, C3, C3.5
C5 | 12 | Now | FA | FALSE | FALSE | FALSE | C1, C2, C3, C3.5, C4
T1 | 1 | At R10 | FA | TRUE | TRUE | TRUE
T2 | 1 | At R10 | FA | TRUE | TRUE | TRUE
T3 | 1 | At R10 | FA | TRUE | TRUE | TRUE
T4 | 4 | At R10 | FA | TRUE | TRUE | TRUE
F1 | 7 | At R10 | FA | TRUE | TRUE | TRUE | C1, C2
F2 | 7 | At R10 | FA | TRUE | TRUE | TRUE | C1, C2
| **Disclaimer - this data does not reflect actual Boeing Production System Data or PI |  |  | FALSE | FALSE | FALSE
BSC1 | 8 | Now | Paint | FALSE | FALSE | FALSE | C1, C2, C3, C3.5, C4 |  | Added for scheduler paint move logic
BSC2 | 8 | Now | Paint | FALSE | FALSE | FALSE | C1, C2, C3, C3.5, C4, C5 |  | Added for scheduler paint move logic

## labor_data
category | shift | team | value
FGI_STAFFING_BYSHIFT | 1 | structure | 16
FGI_STAFFING_BYSHIFT | 1 | systems | 60
FGI_STAFFING_BYSHIFT | 1 | declam | 16
FGI_STAFFING_BYSHIFT | 1 | test | 18
FGI_STAFFING_BYSHIFT | 2 | structure | 6
FGI_STAFFING_BYSHIFT | 2 | systems | 14
FGI_STAFFING_BYSHIFT | 2 | declam | 4
FGI_STAFFING_BYSHIFT | 2 | test | 0
FGI_STAFFING_BYSHIFT | 3 | structure | 0
FGI_STAFFING_BYSHIFT | 3 | systems | 0
FGI_STAFFING_BYSHIFT | 3 | declam | 0
FGI_STAFFING_BYSHIFT | 3 | test | 0
FGI_CPJ |  | structure | 6
FGI_CPJ |  | systems | 3.5
FGI_CPJ |  | declam | 6
FGI_CPJ |  | test | 8
CONFIG |  | STARTDATE | 2024-06-10
CONFIG |  | ENDDATE | 2026-03-10